## Active
Tennessee State University | [18 empty] | 1
Project Tracking Report | [18 empty] | 2
Active and Pending Projects | [18 empty] | 3
2010-06-15 | [18 empty] | 4
5
FM |  |  |  |  | Banner ACCT |  |  |  |  | Funding |  |  |  | Design |  |  |  |  | 6 |  | stars
ACCT # |  |  |  |  | Fund | Org | Prog | Complete | Description | Source | Files | Building/Area | BUDGET | Fee | ADJUSTMENTS | EXPENSES | OBLIGATIONS | FREE BALANCE | 7 |  | project
8
SBC/Capital Outlay (State Funded): | [18 empty] | 9
| 166/ | 001- | 03- | 2006 | 914190 | 20030 | 500 |  | Waterproofing Phase 2 |  |  |  | 647110.08 |  |  |  |  | 647110.08 | 11 |  | 262 | 262 | TSU-SEVERAL BLDGS WINDOW & WAT
| 166/ | 001- | 05- | 2001 | 913105 | 20030 | 500 |  | Avon Williams Security |  |  |  | 800000 |  |  |  |  | 800000 | 13 |  | 246 | 246 | TSU-AVON WILLIAMS-CAMPUS IMPRO
PITS | 166/ | 001- | 02- | 2004A | 913160 | 20030 | 500 |  | Power Plant Upgrades |  |  |  | 882000 |  |  |  |  | 882000 | 14 |  | 250 | 250 | TSU-POWER PLANT MECHANICAL UPD
PITS | 166/ | 001- | 01- | 2007 | 913030 | 20030 | 500 |  | Gentry Storm Drainage |  |  |  | 1250000 |  |  |  |  | 1250000 | 15 |  | 263 | 263 | TSU-GENTRY DRAINAGE CORRECTION
PITS | 166/ | 001- | 01- | 1999 | 914120 | 20030 | 500 |  | ADA Upgrades Phase 3 |  |  |  | 88003 |  |  |  |  | 88003 | 16 |  | 241 | 241 | TSU-ADA IMPROVEMENTS
| 166/ | 001- | 01- | 1999 | 914120 | 20030 | 500 |  | ADA Upgrades Phase 4 |  |  |  | 85000 |  |  |  |  | 85000 | 17 |  | 241 | 241 | TSU-ADA IMPROVEMENTS
PITS | 166/ | 001- | 03- | 2008 | 913110 | 20030 | 500 |  | Various Building Roof Replacements |  |  |  | 1000000 |  |  |  |  | 1000000 | 18 |  | 269 | 269 | TSU-ROOF REPAIR/REPLACEMENT SE
[9 empty] | Boswell HVAC |  |  |  | 2000000 |  |  |  |  | 2000000
[9 empty] | ADA Upgrades 2011 |  |  |  | 90000 |  |  |  |  | 90000 | 20
21
Title III Funded Projects: | [18 empty] | 22
[5 empty] | 913225 | 20030 | 500 |  | Clement Hall Dental Hygiene Upgrade Phase II
[5 empty] | 913220 | 20030 | 500 |  | Performing Arts Center Radio Station Relocation |  |  |  | 1300000 |  |  |  |  | 1300000 | 48
[5 empty] | 913210 | 20030 | 500 |  | Elliott Hall IT Museum Modifications Phase II
[5 empty] | 914150 | 20030 | 500 |  | Performing Arts Center
[5 empty] | 913225 | 20030 | 500 |  | Leftover Funds from Clement |  |  |  | 586000 | [5 empty] | 26
[9 empty] | QEP Writing Center |  |  |  | 160000
USDA Funded Projects: | [18 empty] | 27
PITS | 166/ | 001- | 07- | 2004 | 914020 | 20030 | 500 |  | River Road Farm Facility |  |  |  | 1479716 |  |  |  |  | 1479716 | 29 |  | 253 | 253 | TSU-AGRICULTURAL EXTENSION CEN
[5 empty] | 913030 | 20030 | 500 | [11 empty] | 30
PITS | 166/ | 001- | 07- | 2008 | 914090 | 20030 | 500 |  | Ag Biosecurity-Biotech Building (Planning Only) |  |  |  | 75000 |  |  |  |  | 75000 | 31 |  | 273 | 273 | TSU-CENTER FOR AG BIOTECHNOLOG
32
TSU Residence Life Funded Projects: | [18 empty] | 33
37
TSU Funded Projects: | [18 empty] | 38
PITS | 166/ | 001- | 02- | 2007 | 913055 | 20030 | 500 | H | Hankal Hall Renovation |  |  |  | 1000000 |  |  |  |  | 1000000 | 39 |  | 264 | 264 | TSU-HANKLE HALL RENOVATIONS
PITS | 166/ | 001- | 03- | 2007 | 913200 | 20030 | 500 |  | Football Indoor Practice Facility |  |  |  | 3200000 |  |  |  |  | 3200000 | 40
PITS | 166/ | 001- | 04- | 2008 | 912010 | 20030 | 500 |  | Incubation Center Roof Replacement |  |  |  | 300000 |  |  |  |  | 300000 | 41 |  | 270 | 270 | TSU-NBIC ROOF REPAIRS
44
45
Pending Projects-Awaiting Funding: | [18 empty] | 46
PITS | 166/ | 001- | 04- | 2004 | really still waiting? |  |  |  | Fraternity Monument |  |  |  | 75000 |  |  |  |  | 75000 | 47
Other Funding:
PITS | 166/ | 001- | 01- | 2006 | 913010 | 20030 | 500 |  | Master Plan Update |  |  |  | 360000 |  |  |  |  | 360000
[19 empty] | PROJECT: | 243 | TSU-AGRICULTURE I.T. CTR. NEW |  | 41 | TSU-AGRICULTURE EXTENSION I.T. | SBC: | 166 | 001 | 03 | 00 | #VALUE!
[19 empty] | PROJECT: | 242 | TSU-UTILIY SYSTEMS & TUNNEL RE |  | 40 | TSU-UTILITY SYSTEMS & TUNNEL R | SBC: | 166 | 001 | 01 | 00 | #VALUE!
In House Projects : | [18 empty] | PROJECT: | 246 | TSU-AVON WILLIAMS-CAMPUS IMPRO |  | 44 | TSU-AVON WILLIAMS-CONDITION SU | SBC: | 166 | 001 | 05 | 01 | 246
#VALUE!
#VALUE!
In House Projects that are funded:
#VALUE!
[9 empty] | Clay Hall |  |  |  | 50000 | [5 empty] | PROJECT: | 251 | TSU-HARNED HALL LAB UPGRADE |  | 48 | TSU-HARNED HALL LAB UPGRADE | SBC: | 166 | 001 | 05 | 04 | #VALUE!
[9 empty] | Library |  |  |  | 30000 | [5 empty] | PROJECT: | 250 | TSU-POWER PLANT MECHANICAL UPD |  | 47 | TSU-POWER PLANT MECHANICAL UPD | SBC: | 166 | 001 | 02 | 04 | 250
[5 empty] | 221158 | 17501 | 200 |  | Arts & Sciences Advisement Center |  |  |  | 6722.76 | [5 empty] | PROJECT: | 249 | TSU-MCCORD HALL MECHANICAL & M |  | 46 | TSU-MCCORD HALL MECHANICAL & M | SBC: | 166 | 001 | 01 | 04 | #VALUE!
[19 empty] | PROJECT: | 258 | TSU-CLEMENT HALL ALLIED HEALTH |  | 55 | TSU-CLEMENT HALL ALLIED HEALTH | SBC: | 166 | 001 | 05 | 05 | 258
[19 empty] | PROJECT: | 256 | TSU-ELECTRICAL DISTRIBUTION SY |  | 53 | TSU-ELECTRICAL DISTRIBUTION SY | SBC: | 166 | 001 | 03 | 05 | #VALUE!
[19 empty] | PROJECT: | 255 | TSU-MCCORD & HARNED HALLS UPGR |  | 52 | TSU-MCCORD & HARNED HALLS UPGR | SBC: | 166 | 001 | 02 | 05 | #VALUE!
[19 empty] | PROJECT: | 261 | TSU-STUDENT HOUSING FIRE SUPPR |  | 58 | TSU-STUDENT HOUSING FIRE SUPPR | SBC: | 166 | 001 | 01 | 05 | 261
[19 empty] | PROJECT: | 267 | TSU-HOUSING FIRE SAFETY UPGRAD |  | 64 | TSU-HOUSING FIRE SAFETY UPGRAD | SBC: | 166 | 001 | 04 | 06 | #VALUE!
[19 empty] | PROJECT: | 262 | TSU-SEVERAL BLDGS WINDOW & WAT |  | 59 | TSU-SEVERAL BLDGS WINDOW & WAT | SBC: | 166 | 001 | 03 | 06 | 262
In house Funding |  |  |  |  | 110001 | 23200 | 500 |  | Department Funded Projects | [9 empty] | PROJECT: | 260 | TSU-ELLIOTT HALL EXHIBITION GA |  | 57 | TSU-ELLIOTT HALL EXHIBITION GA | SBC: | 166 | 001 | 02 | 06 | 260
[19 empty] | PROJECT: | 265 | TSU-LAWSON HALL ROOF & UPGRADE |  | 62 | TSU-LAWSON HALL ROOF & UPGRADE | SBC: | 166 | 001 | 04 | 07 | 265
Clompleted Projects | [18 empty] | PROJECT: | 264 | TSU-HANKLE HALL RENOVATIONS |  | 61 | TSU-HANKLE HALL RENOVATIONS | SBC: | 166 | 001 | 02 | 07 | 264
[19 empty] | PROJECT: | 263 | TSU-GENTRY DRAINAGE CORRECTION |  | 60 | TSU-GENTRY DRAINAGE IMPROVEMEN | SBC: | 166 | 001 | 01 | 07 | 263
PITS | 166/ | 001- | 03- | 2006 | 914190 | 20030 | 500 | C | Waterproofing Phase 1 |  |  |  | 2337000 |  |  |  |  | 2337000 | 10 |  | 262 | 262 | TSU-SEVERAL BLDGS WINDOW & WAT
PITS | 166/ | 001- | 02- | 2008 | 913190 | 20030 | 500 | C | Steam Infrastructure Upgrades |  |  |  | 1000000 |  |  |  |  | 1000000 | 19 |  | 268 | 268 | TSU-INFRASTRUCTURE REPAIRS/REP
PITS | 166/ | 001- | 05- | 2005 | 913180 | 20030 | 500 | C | Clement Hall Dental Hygiene Upgrade Phase I |  |  |  | 2713630 | 67695.07 |  |  |  | 2645934.93 | 23 |  | 258 | 258 | TSU-CLEMENT HALL ALLIED HEALTH
PITS | 166/ | 001- | 05- | 2008 | 913185 | 20030 | 500 | C | CIT Infrastructure Upgrades |  |  |  | 1300000 |  |  |  |  | 1300000 | 25 |  | 271 | 271 | TSU-NETWORK INFRASTRUCTURE IMP
PITS | 166/ | 001- | 04- | 2007 | 914100 | 20030 | 500 | C | Lawson Roof Replacement |  |  |  | 184500 |  |  |  |  | 184500 | 28 |  | 265 | 265 | TSU-LAWSON HALL ROOF & UPGRADE
PITS | 166/ | 001- | 01- | 2005 | 914130 | 20030 | 500 | C | Fire Suppression Phase 3 |  |  |  | 1419328 |  |  |  |  | 1419328 | 34 |  | 261 | 261 | TSU-STUDENT HOUSING FIRE SUPPR
PITS | 166/ | 001- | 06- | 2005 | 934000 | 20040 | 500 | C | Wilson Hall Cabinetry and Furniture |  |  |  | 554000 |  |  |  |  | 554000 | 35 |  | 261 | 261 | TSU-STUDENT HOUSING FIRE SUPPR |  |  | 272 | TSU-WILSON HALL INTERIORS UPGR |  | 69 | TSU-WILSON HALL INTERIORS UPGR | SBC: | 166 | 001 | 06 | 08
PITS | 166/ | 001- | 01- | 2008 | 914130 | 20030 | 500 | C | NRC Sanitary Sewer Repair |  |  |  | 230000 |  |  |  |  | 230000 | 36 |  | 266 | 266 | TSU-SANITARY SEWER REPAIRS
[8 empty] | C | Home Renovatons |  |  |  | 53635.8 |  |  |  |  | 53635.8 | PROJECT: | 248 | TSU-ELLIOTT HALL PRESERVATION |  | 45 | TSU-ELLIOTT HALL PRESERVATION | SBC: | 166 | 001 | 01 | 03 | #VALUE!
[8 empty] | C | RASP Gas Line |  |  |  | 4100 | [5 empty] | PROJECT: | 253 | TSU-AGRICULTURAL EXTENSION CEN |  | 50 | TSU-AGRICULTURAL EXTENSION CEN | SBC: | 166 | 001 | 07 | 04 | 253
[5 empty] | 221160 | 13890 | 200 | C | Nursing Conservatory |  |  |  | 7953.06 | [5 empty] | PROJECT: | 259 | TSU-RESIDENCE HALLS RE-ROOFING |  | 56 | TSU-RESIDENCE HALLS RE-ROOFING | SBC: | 166 | 001 | 06 | 05 | #VALUE!
PITS | 166/ | 001- | 02- | 2006 | 914150 | 20030 | 500 |  | Elliott Hall IT Museum Modifications Phase I |  |  |  | 610000 | 1748.47 | 87036.5 |  |  | 521215.03 | 24 |  | 260 | 260 | TSU-ELLIOTT HALL EXHIBITION GA
PITS | 166/ | 001- | 05- | 2001 | 913105 | 20030 | 500 |  | Avon Williams Renovation |  |  |  | 22500000 |  |  |  |  | 22500000 | 12 |  | 246 | 246 | TSU-AVON WILLIAMS-CAMPUS IMPRO
PITS | 166/ | 001- | 02- | 2004 | 913160 | 20030 | 500 |  | Power Plant Upgrades |  |  |  | 2220000 |  |  |  |  | 2220000
PITS | 166/ | 001- | 01- | 1999 | 914120 | 20030 | 500 |  | ADA Upgrades Phase 3 |  |  |  | 88003 |  |  |  |  | 88003 | 16 |  | 241 | 241 | TSU-ADA IMPROVEMENTS
[5 empty] | 223059 | 17041 | 300 | C | Center of Service Learning |  |  |  | 75706.76 |  |  |  |  | 75706.76 | PROJECT: | 245 | TSU-ROOF REPAIRS SEVERAL BUILD |  | 43 | TSU-ROOF REPAIR SEVERAL BUILDI | SBC: | 166 | 001 | 04 | 01
[8 empty] | C | Grace Eaton Daycare |  |  |  | 71662.5 |  |  |  |  | 71662.5 | PROJECT: | 254 | TSU-RASP BLDG |  | 51 | TSU-RASP BLDG | SBC: | 166 | 001 | 02 | 03
[8 empty] | C | Clement Hall Basement HVAC |  |  |  | 70000 | [5 empty] | PROJECT: | 252 | TSU-LRC BATHROOMS UPGRADE |  | 49 | TSU-LRC BATHROOMS UPGRADE | SBC: | 166 | 001 | 06 | 04

## stars nov report
[8 empty] | REPORT-ID: AG05B837-01 STATE OF TENNESSEE ADMIN AGENCY 332.60 |  |  |  |  | 1
[8 empty] | STATEWIDE ACCOUNTING AND REPORTING SYSTEM DIVISION OF HIGHER EDUCATION |  |  |  |  | 2
[8 empty] | PROJECT STATUS REPORT BY OBJECT CODE TENNESSEE BOARD OF REGENTS |  |  |  |  | 3
[8 empty] | 12/13/08 (13:27) PM ACCOUNTING DATE 11/30/08 PAGE 2,034 |  |  |  |  | 4
5
[8 empty] | FUND: 31 CAPITAL PROJECTS FUND RESP LEVEL 1: 31 CAPITAL PROJECTS FUND |  |  |  |  | 6
[8 empty] | DEPARTMENT: 332 DIVISION OF HIGHER EDUCATION RESP LEVEL 2: 15 STATE BOARD OF REGENTS |  |  |  |  | 7
[8 empty] | DIVISION: 77 TENNESSEE STATE UNIVERSITY RESP LEVEL 3: 01 UNIVERSITIES |  |  |  |  | 8
PROJECT: | 233 | TSU NEW PERFORMING ARTS BLDG & |  | 31 | TSU NEW PERFORMING ARTS BLDG & | SBC: | 1660010496 |  |  |  |  | x | 9
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 10
|  |  | RESP LEVEL 6: | [9 empty] | 11
12
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 13
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 14
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 15
16
[8 empty] | 05 UTILITIES AND F 0.00 0.00 0.00 |  |  |  |  | 17
[8 empty] | 0.00 22,000.00 0.00 22,000.00- |  |  |  |  | 18
19
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 20
[8 empty] | 1,002,208.18 1,002,208.18 0.00 0.00 |  |  |  |  | 21
22
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 23
[8 empty] | 500,000.00 712,788.25 0.00 212,788.25- |  |  |  |  | 24
25
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 26
[8 empty] | 9,342,723.27 9,107,935.02 0.00 234,788.25 |  |  |  |  | 27
28
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 29
[8 empty] | 10,844,931.45 0.00 10,844,931.45 10,844,931.45 0.00 0.00 |  |  |  |  | 30
31
32
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 33
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 34
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 35
36
[8 empty] | 890 INTERDEPARTMENTAL 0.00 0.00 0.00 0.00 0.00 |  |  |  |  | 37
38
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 1,452,931.45 1,452,931.45 0.00 |  |  |  |  | 39
40
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 1,452,931.45 1,452,931.45 0.00 |  |  |  |  | 41
42
43
[8 empty] | STATE BONDS |  |  |  |  | 44
45
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 46
47
[8 empty] | B96CH952 CO 342,000.00 |  |  |  |  | 48
49
[8 empty] | B97CH 535 9,050,000.00 |  |  |  |  | 50
51
[8 empty] | TOTAL STATE BONDS 9,392,000.00 |  |  |  |  | 52
53
[8 empty] | GRAND TOTAL FUNDING 10,844,931.45 |  |  |  |  | 54
55
60
PROJECT: | 240 | NORTH CAMPUS IMPROVEMENTS |  | 38 | NORTH CAMPUS IMPROVEMENTS | SBC: | 1660010297 |  |  |  |  | x | 64
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 65
|  |  | RESP LEVEL 6: | [9 empty] | 66
67
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 68
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 69
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 70
71
[8 empty] | 05 UTILITIES AND F 0.00 0.00 0.00 |  |  |  |  | 72
[8 empty] | 0.00 91.73 0.00 91.73- |  |  |  |  | 73
74
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 75
[8 empty] | 500,000.00 503,266.74 0.00 3,266.74- |  |  |  |  | 76
77
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 78
[8 empty] | 300,000.00 229,333.51 0.00 70,666.49 |  |  |  |  | 79
80
[8 empty] | 09 SUPPLIES 0.00 0.00 0.00 |  |  |  |  | 81
[8 empty] | 0.00 232,119.96 0.00 232,119.96- |  |  |  |  | 82
83
[8 empty] | 10 RENTALS AND INS 0.00 0.00 0.00 |  |  |  |  | 84
[8 empty] | 0.00 3,900.00 0.00 3,900.00- |  |  |  |  | 85
86
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 87
[8 empty] | 0.00 38,408.17 0.00 38,408.17- |  |  |  |  | 88
89
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 90
[8 empty] | 600,000.00 465,514.77 0.00 134,485.23 |  |  |  |  | 91
92
[8 empty] | 20 HIGHWAY CONSTRU 0.00 0.00 0.00 |  |  |  |  | 93
[8 empty] | 3,020,000.00 2,708,462.32 0.00 311,537.68 |  |  |  |  | 94
95
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 96
[8 empty] | 0.00 2,325.00 0.00 2,325.00- |  |  |  |  | 97
98
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 99
[8 empty] | 4,420,000.00 0.00 4,420,000.00 4,183,422.20 0.00 236,577.80 |  |  |  |  | 100
101
102
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 103
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 104
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 105
106
[8 empty] | 890 INTERDEPARTMENTAL 0.00 0.00 425,000.00 425,000.00 0.00 |  |  |  |  | 107
108
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 3,995,000.00 3,758,422.20 236,577.80 |  |  |  |  | 126
127
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 4,420,000.00 4,183,422.20 236,577.80 |  |  |  |  | 128
129
[8 empty] | GRAND TOTAL FUNDING 4,420,000.00 |  |  |  |  | 130
131
136
PROJECT: | 241 | TSU-ADA IMPROVEMENTS |  | 39 | TSU-ADA IMPROVEMENTS | SBC: | 1660010199 | [5 empty] | 140
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 141
|  |  | RESP LEVEL 6: | [9 empty] | 142
143
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 144
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 145
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 146
147
[8 empty] | 07 MAINT., REPAIRS 81,000.00 0.00 0.00 |  |  |  |  | 148
[8 empty] | 785,000.00 188,785.74 0.00 596,214.26 |  |  |  |  | 149
150
[8 empty] | 08 PROFESSIONAL AN 4,000.00 0.00 9,255.99 |  |  |  |  | 151
[8 empty] | 112,052.00 110,461.64 0.00 7,665.63- |  |  |  |  | 152
153
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 154
[8 empty] | 0.00 320,908.66 0.00 320,908.66- |  |  |  |  | 155
156
[8 empty] | RESP6 LEVEL TOTAL 85,000.00 0.00 9,255.99 |  |  |  |  | 157
[8 empty] | 897,052.00 0.00 897,052.00 620,156.04 0.00 267,639.97 |  |  |  |  | 158
159
160
[8 empty] | STATE BONDS |  |  |  |  | 161
162
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 163
164
[8 empty] | F33260B98CH1103ADA 145,129.00 |  |  |  |  | 165
166
[8 empty] | F35502B00CH984 ADA 94,904.00 |  |  |  |  | 167
168
[8 empty] | F35502B99CH401 ADA 87,585.00 |  |  |  |  | 169
170
[8 empty] | TOTAL STATE BONDS 327,618.00 |  |  |  |  | 171
172
173
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 174
175
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 176
177
[8 empty] | F33260C03CH842ADA 88,003.00 |  |  |  |  | 178
179
[8 empty] | F33260C08CH603ADA 88,003.00 |  |  |  |  | 180
181
[8 empty] | F35502C00CH1135ADA 418.00 |  |  |  |  | 182
183
[8 empty] | F35502C00CH539ADA 44,001.00 |  |  |  |  | 201
202
[8 empty] | F35502C05CH961ADA 88,003.00 |  |  |  |  | 203
204
[8 empty] | F35502C06CH503ADA 88,003.00 |  |  |  |  | 205
206
[8 empty] | F35502C07CH963ADA 88,003.00 |  |  |  |  | 207
208
[8 empty] | F35502C09CH1203MAINT 85,000.00 |  |  |  |  | 209
210
[8 empty] | TOTAL CURRENT FUNDS 569,434.00 |  |  |  |  | 211
212
[8 empty] | GRAND TOTAL FUNDING 897,052.00 |  |  |  |  | 213
214
219
PROJECT: | 242 | TSU-UTILIY SYSTEMS & TUNNEL RE |  | 40 | TSU-UTILITY SYSTEMS & TUNNEL R | SBC: | 1660010100 |  |  |  |  | x | 223
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 224
|  |  | RESP LEVEL 6: | [9 empty] | 225
226
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 227
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 228
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 229
230
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 231
[8 empty] | 714,131.54 714,131.54 0.00 0.00 |  |  |  |  | 232
233
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 234
[8 empty] | 92,322.45 92,322.45 0.00 0.00 |  |  |  |  | 235
236
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 237
[8 empty] | 806,453.99 0.00 806,453.99 806,453.99 0.00 0.00 |  |  |  |  | 238
239
240
[8 empty] | STATE BONDS |  |  |  |  | 241
242
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 243
244
[8 empty] | F33260B00CH984 MAINT 950,000.00 |  |  |  |  | 245
246
[8 empty] | T33260B00CH984MAINT 143,546.01- |  |  |  |  | 247
248
[8 empty] | TOTAL STATE BONDS 806,453.99 |  |  |  |  | 249
250
251
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 252
253
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 254
255
[8 empty] | F33260C01CH994 MAINT 50,000.00 |  |  |  |  | 256
257
[8 empty] | T33260C01CH994MAINT 50,000.00- |  |  |  |  | 258
259
[8 empty] | TOTAL CURRENT FUNDS 0.00 |  |  |  |  | 260
261
[8 empty] | GRAND TOTAL FUNDING 806,453.99 |  |  |  |  | 262
263
268
PROJECT: | 243 | TSU-AGRICULTURE I.T. CTR. NEW |  | 41 | TSU-AGRICULTURE EXTENSION I.T. | SBC: | 1660010300 |  |  |  |  | x | 272
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 273
|  |  | RESP LEVEL 6: | [9 empty] | 274
275
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 276
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 277
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 278
279
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 280
[8 empty] | 0.00 361,134.72 0.00 361,134.72- |  |  |  |  | 281
282
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 4,195.53 |  |  |  |  | 283
[8 empty] | 232,733.00 187,086.16 0.00 41,451.31 |  |  |  |  | 284
285
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 286
[8 empty] | 267,267.00 290,480.00 0.00 23,213.00- |  |  |  |  | 287
288
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 289
[8 empty] | 1,600,000.00 849,764.02 0.00 750,235.98 |  |  |  |  | 290
291
[8 empty] | 20 HIGHWAY CONSTRU 0.00 0.00 0.00 |  |  |  |  | 292
[8 empty] | 0.00 352,662.61 0.00 352,662.61- |  |  |  |  | 293
294
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 295
[8 empty] | 0.00 300.00 0.00 300.00- |  |  |  |  | 296
297
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 4,195.53 |  |  |  |  | 298
[8 empty] | 2,100,000.00 0.00 2,100,000.00 2,041,427.51 0.00 54,376.96 |  |  |  |  | 299
300
301
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 302
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 303
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 304
305
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 2,100,000.00 2,041,427.51 58,572.49 |  |  |  |  | 306
307
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 2,100,000.00 2,041,427.51 58,572.49 |  |  |  |  | 308
309
[8 empty] | GRAND TOTAL FUNDING 2,100,000.00 |  |  |  |  | 310
311
316
PROJECT: | 245 | TSU-ROOF REPAIRS SEVERAL BUILD |  | 43 | TSU-ROOF REPAIR SEVERAL BUILDI | SBC: | 1660010401 |  |  |  |  | x | 320
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 321
|  |  | RESP LEVEL 6: | [9 empty] | 322
323
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 324
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 325
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 326
327
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 328
[8 empty] | 1,000,306.31 1,000,306.31 0.00 0.00 |  |  |  |  | 329
330
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 331
[8 empty] | 100,400.55 100,400.55 0.00 0.00 |  |  |  |  | 332
333
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 334
[8 empty] | 1,100,706.86 0.00 1,100,706.86 1,100,706.86 0.00 0.00 |  |  |  |  | 335
336
337
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 338
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 339
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 340
341
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 90,706.86 90,706.86 0.00 |  |  |  |  | 342
343
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 90,706.86 90,706.86 0.00 |  |  |  |  | 344
345
346
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 347
348
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 349
350
[8 empty] | F35502C02CH435MAINT 1,010,000.00 |  |  |  |  | 351
352
[8 empty] | TOTAL CURRENT FUNDS 1,010,000.00 |  |  |  |  | 353
354
[8 empty] | GRAND TOTAL FUNDING 1,100,706.86 |  |  |  |  | 355
356
361
PROJECT: | 246 | TSU-AVON WILLIAMS-CAMPUS IMPRO |  | 44 | TSU-AVON WILLIAMS-CONDITION SU | SBC: | 1660010501 | [5 empty] | 365
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 366
|  |  | RESP LEVEL 6: | [9 empty] | 367
368
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 369
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 370
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 371
372
[8 empty] | 07 MAINT., REPAIRS 580,000.00 0.00 3,954.60 |  |  |  |  | 373
[8 empty] | 1,846,829.02 2,123,075.92 0.00 280,201.50- |  |  |  |  | 374
375
[8 empty] | 08 PROFESSIONAL AN 0.00 15,315.76 11,388.14 |  |  |  |  | 376
[8 empty] | 2,379,180.00 2,045,292.30 0.00 322,499.56 |  |  |  |  | 377
378
[8 empty] | 09 SUPPLIES 0.00 0.00 194.88 |  |  |  |  | 379
[8 empty] | 0.00 240,393.14 0.00 240,588.02- |  |  |  |  | 380
381
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 382
[8 empty] | 1,505,001.00 909,635.89 0.00 595,365.11 |  |  |  |  | 383
384
[8 empty] | 18 BUILDINGS 0.00 0.00 426,502.20 |  |  |  |  | 385
[8 empty] | 17,589,735.92 16,493,484.85 0.00 669,748.87 |  |  |  |  | 386
387
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 388
[8 empty] | 0.00 12,284.75 0.00 12,284.75- |  |  |  |  | 389
390
[8 empty] | RESP6 LEVEL TOTAL 580,000.00 15,315.76 442,039.82 |  |  |  |  | 391
[8 empty] | 23,320,745.94 0.00 23,320,745.94 21,824,166.85 0.00 1,054,539.27 |  |  |  |  | 392
393
394
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 395
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 396
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 397
398
[8 empty] | 890 INTERDEPARTMENTAL 0.00 0.00 103,832.89 103,832.89 0.00 |  |  |  |  | 399
400
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 940,181.00 825,181.00 115,000.00 |  |  |  |  | 401
402
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 1,044,013.89 929,013.89 115,000.00 |  |  |  |  | 403
404
405
[8 empty] | STATE BONDS |  |  |  |  | 406
407
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 425
426
[8 empty] | B02CH852CANC07 5,461,000.00- |  |  |  |  | 427
428
[8 empty] | B02CH852CAUC08 2,239,000.00- |  |  |  |  | 429
430
[8 empty] | B02CH852UNALL 8,500,000.00 |  |  |  |  | 431
432
[8 empty] | B96CH952UNALL 283,735.92 |  |  |  |  | 433
434
[8 empty] | F33213B02CH852CO 3,100,000.00 |  |  |  |  | 435
436
[8 empty] | F33260B02CH852MAINT 1,250,000.00 |  |  |  |  | 437
438
[8 empty] | F33260B06CH962MAINT 570,000.00 |  |  |  |  | 439
440
[8 empty] | F33260B07CH591MAINT 580,000.00 |  |  |  |  | 441
442
[8 empty] | TOTAL STATE BONDS 6,583,735.92 |  |  |  |  | 443
444
445
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 446
447
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 448
449
[8 empty] | C02CH852CANC07 5,461,000.00 |  |  |  |  | 450
451
[8 empty] | C02CH852CAUC08 2,239,000.00 |  |  |  |  | 452
453
[8 empty] | C09CH1203MAINT 580,000.00 |  |  |  |  | 454
455
[8 empty] | F33213C02CH435COEIER 150,000.00 |  |  |  |  | 456
457
[8 empty] | F33213C03CH842GEIER 750,000.00 |  |  |  |  | 458
459
[8 empty] | F33213C04CH356GEIER 1,500,000.00 |  |  |  |  | 460
461
[8 empty] | F33213C05CH961GEIER 2,500,000.00 |  |  |  |  | 479
480
[8 empty] | F33213C07CH963GEIER 2,500,000.00 |  |  |  |  | 481
482
[8 empty] | F33260C03CH842MAINT 50,000.00 |  |  |  |  | 483
484
[8 empty] | F33260C07CH963MAINT 10,000.00 |  |  |  |  | 485
486
[8 empty] | T33260C03CH842MAINT 47,003.87- |  |  |  |  | 487
488
[8 empty] | TOTAL CURRENT FUNDS 15,692,996.13 |  |  |  |  | 489
490
[8 empty] | GRAND TOTAL FUNDING 23,320,745.94 |  |  |  |  | 491
492
497
PROJECT: | 248 | TSU-ELLIOTT HALL PRESERVATION |  | 45 | TSU-ELLIOTT HALL PRESERVATION | SBC: | 1660010103 |  |  |  |  | x | 501
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 502
|  |  | RESP LEVEL 6: | [9 empty] | 503
504
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 505
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 506
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 507
508
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 509
[8 empty] | 472,533.72 472,533.72 0.00 0.00 |  |  |  |  | 510
511
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 512
[8 empty] | 62,496.61 62,496.61 0.00 0.00 |  |  |  |  | 513
514
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 515
[8 empty] | 404.00 404.00 0.00 0.00 |  |  |  |  | 516
517
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 518
[8 empty] | 535,434.33 0.00 535,434.33 535,434.33 0.00 0.00 |  |  |  |  | 519
520
521
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 522
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 523
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 524
525
[8 empty] | 880 CURRENT SERVICES 0.00 0.00 30,318.66 30,318.66 0.00 |  |  |  |  | 526
527
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 319,030.00 319,030.00 0.00 |  |  |  |  | 528
529
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 349,348.66 349,348.66 0.00 |  |  |  |  | 530
531
532
[8 empty] | STATE BONDS |  |  |  |  | 533
534
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 535
536
[8 empty] | B96CH952UNALL 19,196.77 |  |  |  |  | 537
538
[8 empty] | TOTAL STATE BONDS 19,196.77 |  |  |  |  | 539
540
541
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 542
543
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 544
545
[8 empty] | C89CH563UNALL 8,295.60 |  |  |  |  | 563
564
[8 empty] | C90CH1085UNALL 31,663.09 |  |  |  |  | 565
566
[8 empty] | C92CH1018UNALL 164,555.88 |  |  |  |  | 567
568
[8 empty] | T33260C92CH1018UNALL 37,625.67- |  |  |  |  | 569
570
[8 empty] | TOTAL CURRENT FUNDS 166,888.90 |  |  |  |  | 571
572
[8 empty] | GRAND TOTAL FUNDING 535,434.33 |  |  |  |  | 573
574
579
PROJECT: | 249 | TSU-MCCORD HALL MECHANICAL & M |  | 46 | TSU-MCCORD HALL MECHANICAL & M | SBC: | 1660010104 |  |  |  |  | x | 583
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 584
|  |  | RESP LEVEL 6: | [9 empty] | 585
586
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 587
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 588
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 589
590
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 591
[8 empty] | 397,667.03 397,667.03 0.00 0.00 |  |  |  |  | 592
593
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 594
[8 empty] | 62,449.71 62,449.71 0.00 0.00 |  |  |  |  | 595
596
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 597
[8 empty] | 460,116.74 0.00 460,116.74 460,116.74 0.00 0.00 |  |  |  |  | 598
599
600
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 601
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 602
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 603
604
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 460,116.74 460,116.74 0.00 |  |  |  |  | 605
606
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 460,116.74 460,116.74 0.00 |  |  |  |  | 607
608
[8 empty] | GRAND TOTAL FUNDING 460,116.74 |  |  |  |  | 609
610
615
PROJECT: | 250 | TSU-POWER PLANT MECHANICAL UPD |  | 47 | TSU-POWER PLANT MECHANICAL UPD | SBC: | 1660010204 | [5 empty] | 619
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 620
|  |  | RESP LEVEL 6: | [9 empty] | 621
622
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 623
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 624
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 625
626
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 627
[8 empty] | 2,765,000.00 137,200.00 0.00 2,627,800.00 |  |  |  |  | 628
629
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 72,114.17 |  |  |  |  | 630
[8 empty] | 345,000.00 219,723.08 0.00 53,162.75 |  |  |  |  | 631
632
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 633
[8 empty] | 0.00 1,739,914.10 0.00 1,739,914.10- |  |  |  |  | 634
635
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 636
[8 empty] | 0.00 1,168.75 0.00 1,168.75- |  |  |  |  | 637
638
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 72,114.17 |  |  |  |  | 639
[8 empty] | 3,110,000.00 0.00 3,110,000.00 2,098,005.93 0.00 939,879.90 |  |  |  |  | 640
641
642
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 643
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 644
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 645
646
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 6,690.00 0.00 6,690.00 6,690.00- |  |  |  |  | 647
648
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 6,690.00 0.00 6,690.00 6,690.00- |  |  |  |  | 649
650
651
[8 empty] | STATE BONDS |  |  |  |  | 652
653
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 654
655
[8 empty] | F33260B04CH958MAINT 3,000,000.00 |  |  |  |  | 656
657
[8 empty] | TOTAL STATE BONDS 3,000,000.00 |  |  |  |  | 658
659
660
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 661
662
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 680
681
[8 empty] | F33260C05CH961MAINT 110,000.00 |  |  |  |  | 682
683
[8 empty] | TOTAL CURRENT FUNDS 110,000.00 |  |  |  |  | 684
685
[8 empty] | GRAND TOTAL FUNDING 3,110,000.00 |  |  |  |  | 686
687
692
PROJECT: | 251 | TSU-HARNED HALL LAB UPGRADE |  | 48 | TSU-HARNED HALL LAB UPGRADE | SBC: | 1660010504 |  |  |  |  | x | 696
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 697
|  |  | RESP LEVEL 6: | [9 empty] | 698
699
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 700
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 701
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 702
703
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 704
[8 empty] | 75,074.15 75,074.15 0.00 0.00 |  |  |  |  | 705
706
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 707
[8 empty] | 16,684.60 16,684.60 0.00 0.00 |  |  |  |  | 708
709
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 710
[8 empty] | 86.50 86.50 0.00 0.00 |  |  |  |  | 711
712
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 713
[8 empty] | 91,845.25 0.00 91,845.25 91,845.25 0.00 0.00 |  |  |  |  | 714
715
716
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 717
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 718
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 719
720
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 91,845.25 91,845.25 0.00 |  |  |  |  | 721
722
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 91,845.25 91,845.25 0.00 |  |  |  |  | 723
724
[8 empty] | GRAND TOTAL FUNDING 91,845.25 |  |  |  |  | 725
726
731
PROJECT: | 252 | TSU-LRC BATHROOMS UPGRADE |  | 49 | TSU-LRC BATHROOMS UPGRADE | SBC: | 1660010604 |  |  |  |  | x | 735
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 736
|  |  | RESP LEVEL 6: | [9 empty] | 737
738
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 739
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 740
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 741
742
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 743
[8 empty] | 0.00 0.00 0.00 0.00 |  |  |  |  | 744
745
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 746
[8 empty] | 25,836.36 25,836.36 0.00 0.00 |  |  |  |  | 747
748
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 749
[8 empty] | 208,842.29 208,842.29 0.00 0.00 |  |  |  |  | 750
751
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 752
[8 empty] | 233.50 233.50 0.00 0.00 |  |  |  |  | 753
754
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 755
[8 empty] | 234,912.15 0.00 234,912.15 234,912.15 0.00 0.00 |  |  |  |  | 756
757
758
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 759
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 760
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 761
762
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 234,912.15 234,912.15 0.00 |  |  |  |  | 763
764
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 234,912.15 234,912.15 0.00 |  |  |  |  | 765
766
[8 empty] | GRAND TOTAL FUNDING 234,912.15 |  |  |  |  | 767
768
773
PROJECT: | 253 | TSU-AGRICULTURAL EXTENSION CEN |  | 50 | TSU-AGRICULTURAL EXTENSION CEN | SBC: | 1660010704 | [5 empty] | 777
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 778
|  |  | RESP LEVEL 6: | [9 empty] | 779
780
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 781
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 782
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 783
784
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 77,617.00 |  |  |  |  | 785
[8 empty] | 224,716.56 47,504.24 0.00 99,595.32 |  |  |  |  | 786
787
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 788
[8 empty] | 145,000.00 0.00 0.00 145,000.00 |  |  |  |  | 789
790
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 791
[8 empty] | 1,110,000.00 0.00 0.00 1,110,000.00 |  |  |  |  | 792
793
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 77,617.00 |  |  |  |  | 794
[8 empty] | 1,479,716.56 0.00 1,479,716.56 47,504.24 0.00 1,354,595.32 |  |  |  |  | 795
796
797
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 798
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 799
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 800
801
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 1,479,716.56 47,504.24 1,432,212.32 |  |  |  |  | 802
803
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 1,479,716.56 47,504.24 1,432,212.32 |  |  |  |  | 804
805
[8 empty] | GRAND TOTAL FUNDING 1,479,716.56 |  |  |  |  | 806
807
812
PROJECT: | 254 | TSU-RASP BLDG |  | 51 | TSU-RASP BLDG | SBC: | 1660010203 |  |  |  |  | x | 816
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 817
|  |  | RESP LEVEL 6: | [9 empty] | 818
819
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 820
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 821
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 822
823
[8 empty] | 08 PROFESSIONAL AN 0.00 68.40 0.00 |  |  |  |  | 824
[8 empty] | 823,000.00 47,129.06 0.00 775,870.94 |  |  |  |  | 825
826
[8 empty] | 09 SUPPLIES 0.00 0.00 3,532.32 |  |  |  |  | 827
[8 empty] | 0.00 22,267.68 0.00 25,800.00- |  |  |  |  | 828
829
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 830
[8 empty] | 0.00 232,030.40 0.00 232,030.40- |  |  |  |  | 831
832
[8 empty] | 18 BUILDINGS 0.00 22,497.30 0.00 |  |  |  |  | 833
[8 empty] | 317,000.00 796,774.03 0.00 479,774.03- |  |  |  |  | 834
835
[8 empty] | 25 PROFESSIONAL SE 0.00 0.00 0.00 |  |  |  |  | 836
[8 empty] | 0.00 6,175.00 0.00 6,175.00- |  |  |  |  | 837
838
[8 empty] | RESP6 LEVEL TOTAL 0.00 22,565.70 3,532.32 |  |  |  |  | 839
[8 empty] | 1,140,000.00 0.00 1,140,000.00 1,104,376.17 0.00 32,091.51 |  |  |  |  | 840
841
842
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 843
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 844
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 845
846
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 300,000.00 300,000.00 0.00 |  |  |  |  | 847
848
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 300,000.00 300,000.00 0.00 |  |  |  |  | 849
850
851
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 852
853
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 854
855
[8 empty] | F33213C07CH963GEIER 840,000.00 |  |  |  |  | 856
857
[8 empty] | TOTAL CURRENT FUNDS 840,000.00 |  |  |  |  | 858
859
[8 empty] | GRAND TOTAL FUNDING 1,140,000.00 |  |  |  |  | 860
861
866
PROJECT: | 255 | TSU-MCCORD & HARNED HALLS UPGR |  | 52 | TSU-MCCORD & HARNED HALLS UPGR | SBC: | 1660010205 |  |  |  |  | x | 870
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 871
|  |  | RESP LEVEL 6: | [9 empty] | 872
873
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 874
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 875
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 876
877
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 878
[8 empty] | 321,464.56 321,464.56 0.00 0.00 |  |  |  |  | 879
880
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 881
[8 empty] | 39,691.70 39,691.70 0.00 0.00 |  |  |  |  | 882
883
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 884
[8 empty] | 0.00 0.00 0.00 0.00 |  |  |  |  | 885
886
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 887
[8 empty] | 361,156.26 0.00 361,156.26 361,156.26 0.00 0.00 |  |  |  |  | 888
889
890
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 891
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 892
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 893
894
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 361,156.26 361,156.26 0.00 |  |  |  |  | 895
896
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 361,156.26 361,156.26 0.00 |  |  |  |  | 897
898
[8 empty] | GRAND TOTAL FUNDING 361,156.26 |  |  |  |  | 899
900
905
PROJECT: | 256 | TSU-ELECTRICAL DISTRIBUTION SY |  | 53 | TSU-ELECTRICAL DISTRIBUTION SY | SBC: | 1660010305 |  |  |  |  | x | 909
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 910
|  |  | RESP LEVEL 6: | [9 empty] | 911
912
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 913
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 914
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 915
916
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 917
[8 empty] | 1,715,096.95 1,715,096.95 0.00 0.00 |  |  |  |  | 918
919
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 920
[8 empty] | 164,903.05 162,566.26 0.00 2,336.79 |  |  |  |  | 921
922
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 923
[8 empty] | 1,880,000.00 0.00 1,880,000.00 1,877,663.21 0.00 2,336.79 |  |  |  |  | 924
925
926
[8 empty] | STATE BONDS |  |  |  |  | 927
928
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 929
930
[8 empty] | F33260B05CH501MAINT 1,800,000.00 |  |  |  |  | 931
932
[8 empty] | TOTAL STATE BONDS 1,800,000.00 |  |  |  |  | 933
934
935
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 936
937
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 938
939
[8 empty] | F33260C06CH503MAINT 80,000.00 |  |  |  |  | 940
941
[8 empty] | TOTAL CURRENT FUNDS 80,000.00 |  |  |  |  | 942
943
[8 empty] | GRAND TOTAL FUNDING 1,880,000.00 |  |  |  |  | 944
945
950
PROJECT: | 258 | TSU-CLEMENT HALL ALLIED HEALTH |  | 55 | TSU-CLEMENT HALL ALLIED HEALTH | SBC: | 1660010505 | [5 empty] | 954
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 955
|  |  | RESP LEVEL 6: | [9 empty] | 956
957
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 958
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 959
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 960
961
[8 empty] | 08 PROFESSIONAL AN 30,000.00 0.00 27,106.20 |  |  |  |  | 962
[8 empty] | 200,000.00 59,774.82 0.00 113,118.98 |  |  |  |  | 963
964
[8 empty] | 09 SUPPLIES 50,000.00 0.00 0.00 |  |  |  |  | 965
[8 empty] | 50,000.00 111.60 0.00 49,888.40 |  |  |  |  | 966
967
[8 empty] | 16 EQUIPMENT 0.00 0.00 0.00 |  |  |  |  | 968
[8 empty] | 350,000.00 0.00 0.00 350,000.00 |  |  |  |  | 969
970
[8 empty] | 18 BUILDINGS 1,233,630.00 0.00 0.00 |  |  |  |  | 971
[8 empty] | 2,113,630.00 0.00 0.00 2,113,630.00 |  |  |  |  | 972
973
[8 empty] | RESP6 LEVEL TOTAL 1,313,630.00 0.00 27,106.20 |  |  |  |  | 974
[8 empty] | 2,713,630.00 0.00 2,713,630.00 59,886.42 0.00 2,626,637.38 |  |  |  |  | 975
976
977
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 978
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 979
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 980
981
[8 empty] | 895 INTERDEPARTMENTAL- C 1,313,630.00 6,690.00- 2,713,630.00 53,196.42 2,660,433.58 |  |  |  |  | 982
983
[8 empty] | TOTAL DEPARTMENTAL REVENUE 1,313,630.00 6,690.00- 2,713,630.00 53,196.42 2,660,433.58 |  |  |  |  | 984
985
[8 empty] | GRAND TOTAL FUNDING 2,713,630.00 |  |  |  |  | 986
987
992
PROJECT: | 259 | TSU-RESIDENCE HALLS RE-ROOFING |  | 56 | TSU-RESIDENCE HALLS RE-ROOFING | SBC: | 1660010605 |  |  |  |  | x | 996
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 997
|  |  | RESP LEVEL 6: | [9 empty] | 998
999
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1000
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1001
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1002
1003
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 1004
[8 empty] | 239,170.00 239,170.00 0.00 0.00 |  |  |  |  | 1005
1006
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 1007
[8 empty] | 30,540.48 30,540.48 0.00 0.00 |  |  |  |  | 1008
1009
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 1010
[8 empty] | 269,710.48 0.00 269,710.48 269,710.48 0.00 0.00 |  |  |  |  | 1011
1012
1013
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1014
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1015
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1016
1017
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 269,710.48 269,710.48 0.00 |  |  |  |  | 1018
1019
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 269,710.48 269,710.48 0.00 |  |  |  |  | 1020
1021
[8 empty] | GRAND TOTAL FUNDING 269,710.48 |  |  |  |  | 1022
1023
1028
PROJECT: | 260 | TSU-ELLIOTT HALL EXHIBITION GA |  | 57 | TSU-ELLIOTT HALL EXHIBITION GA | SBC: | 1660010206 | [5 empty] | 1032
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1033
|  |  | RESP LEVEL 6: | [9 empty] | 1034
1035
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1036
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1037
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1038
1039
[8 empty] | 08 PROFESSIONAL AN 0.00 6,882.07 8,735.00 |  |  |  |  | 1040
[8 empty] | 60,000.00 44,416.10 0.00 6,848.90 |  |  |  |  | 1041
1042
[8 empty] | 16 EQUIPMENT 0.00 0.00 193,194.00 |  |  |  |  | 1043
[8 empty] | 250,000.00 0.00 0.00 56,806.00 |  |  |  |  | 1044
1045
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 1046
[8 empty] | 300,000.00 0.00 0.00 300,000.00 |  |  |  |  | 1047
1048
[8 empty] | RESP6 LEVEL TOTAL 0.00 6,882.07 201,929.00 |  |  |  |  | 1049
[8 empty] | 610,000.00 0.00 610,000.00 44,416.10 0.00 363,654.90 |  |  |  |  | 1050
1051
1052
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1053
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1054
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1055
1056
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 610,000.00 37,534.03 572,465.97 |  |  |  |  | 1057
1058
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 610,000.00 37,534.03 572,465.97 |  |  |  |  | 1059
1060
[8 empty] | GRAND TOTAL FUNDING 610,000.00 |  |  |  |  | 1061
1062
1067
PROJECT: | 261 | TSU-STUDENT HOUSING FIRE SUPPR |  | 58 | TSU-STUDENT HOUSING FIRE SUPPR | SBC: | 1660010105 | [5 empty] | 1071
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1072
|  |  | RESP LEVEL 6: | [9 empty] | 1073
1074
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1075
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1076
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1077
1078
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 4,483.00 |  |  |  |  | 1079
[8 empty] | 67,153.87 22,903.12 0.00 39,767.75 |  |  |  |  | 1080
1081
[8 empty] | 18 BUILDINGS 0.00 0.00 485.67 |  |  |  |  | 1082
[8 empty] | 182,846.13 182,360.46 0.00 0.00 |  |  |  |  | 1083
1084
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 4,968.67 |  |  |  |  | 1085
[8 empty] | 250,000.00 0.00 250,000.00 205,263.58 0.00 39,767.75 |  |  |  |  | 1086
1087
1088
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1089
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1090
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1091
1092
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 250,000.00 205,263.58 44,736.42 |  |  |  |  | 1093
1094
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 250,000.00 205,263.58 44,736.42 |  |  |  |  | 1095
1096
[8 empty] | GRAND TOTAL FUNDING 250,000.00 |  |  |  |  | 1097
1098
1103
PROJECT: | 262 | TSU-SEVERAL BLDGS WINDOW & WAT |  | 59 | TSU-SEVERAL BLDGS WINDOW & WAT | SBC: | 1660010306 | [5 empty] | 1107
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1108
|  |  | RESP LEVEL 6: | [9 empty] | 1109
1110
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1111
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1112
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1113
1114
[8 empty] | 07 MAINT., REPAIRS 0.00 135,233.69 86,039.61 |  |  |  |  | 1115
[8 empty] | 2,770,000.00 1,896,287.53 0.00 787,672.86 |  |  |  |  | 1116
1117
[8 empty] | 08 PROFESSIONAL AN 0.00 12,227.71 29,787.67 |  |  |  |  | 1118
[8 empty] | 350,000.00 218,942.71 0.00 101,269.62 |  |  |  |  | 1119
1120
[8 empty] | RESP6 LEVEL TOTAL 0.00 147,461.40 115,827.28 |  |  |  |  | 1121
[8 empty] | 3,120,000.00 0.00 3,120,000.00 2,115,230.24 0.00 888,942.48 |  |  |  |  | 1122
1123
1124
[8 empty] | STATE BONDS |  |  |  |  | 1125
1126
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1127
1128
[8 empty] | F33260B06CH962MAINT 2,000,000.00 |  |  |  |  | 1129
1130
[8 empty] | F33260B07CH591MAINT 920,000.00 |  |  |  |  | 1131
1132
[8 empty] | TOTAL STATE BONDS 2,920,000.00 |  |  |  |  | 1133
1134
1135
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1136
1137
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1138
1139
[8 empty] | F33260C07CH963MAINT 200,000.00 |  |  |  |  | 1140
1141
[8 empty] | TOTAL CURRENT FUNDS 200,000.00 |  |  |  |  | 1142
1143
[8 empty] | GRAND TOTAL FUNDING 3,120,000.00 |  |  |  |  | 1144
1145
1150
PROJECT: | 263 | TSU-GENTRY DRAINAGE CORRECTION |  | 60 | TSU-GENTRY DRAINAGE IMPROVEMEN | SBC: | 1660010107 | [5 empty] | 1154
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1155
|  |  | RESP LEVEL 6: | [9 empty] | 1156
1157
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1158
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1159
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1160
1161
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 1162
[8 empty] | 1,100,000.00 0.00 0.00 1,100,000.00 |  |  |  |  | 1163
1164
[8 empty] | 08 PROFESSIONAL AN 0.00 14,680.83 83,628.95 |  |  |  |  | 1165
[8 empty] | 150,000.00 20,936.28 0.00 45,434.77 |  |  |  |  | 1166
1167
[8 empty] | RESP6 LEVEL TOTAL 0.00 14,680.83 83,628.95 |  |  |  |  | 1168
[8 empty] | 1,250,000.00 0.00 1,250,000.00 20,936.28 0.00 1,145,434.77 |  |  |  |  | 1169
1170
1171
[8 empty] | STATE BONDS |  |  |  |  | 1172
1173
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1174
1175
[8 empty] | F33260B07CH591MAINT 1,000,000.00 |  |  |  |  | 1176
1177
[8 empty] | TOTAL STATE BONDS 1,000,000.00 |  |  |  |  | 1178
1179
1180
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1181
1182
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1183
1184
[8 empty] | F33260C08CH603MAINT 250,000.00 |  |  |  |  | 1185
1186
[8 empty] | TOTAL CURRENT FUNDS 250,000.00 |  |  |  |  | 1187
1188
[8 empty] | GRAND TOTAL FUNDING 1,250,000.00 |  |  |  |  | 1189
1190
1195
PROJECT: | 264 | TSU-HANKLE HALL RENOVATIONS |  | 61 | TSU-HANKLE HALL RENOVATIONS | SBC: | 1660010207 | [5 empty] | 1199
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1200
|  |  | RESP LEVEL 6: | [9 empty] | 1201
1202
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1203
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1204
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1205
1206
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 47,931.00 |  |  |  |  | 1207
[8 empty] | 125,000.00 32,829.00 0.00 44,240.00 |  |  |  |  | 1208
1209
[8 empty] | 18 BUILDINGS 0.00 0.00 0.00 |  |  |  |  | 1210
[8 empty] | 875,000.00 0.00 0.00 875,000.00 |  |  |  |  | 1211
1212
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 47,931.00 |  |  |  |  | 1213
[8 empty] | 1,000,000.00 0.00 1,000,000.00 32,829.00 0.00 919,240.00 |  |  |  |  | 1214
1215
1216
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1217
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1218
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1219
1220
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 497,740.70 0.00 497,740.70 |  |  |  |  | 1221
1222
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 497,740.70 0.00 497,740.70 |  |  |  |  | 1223
1224
1225
[8 empty] | STATE BONDS |  |  |  |  | 1226
1227
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1228
1229
[8 empty] | F33260B00CH984MAINT 143,546.01 |  |  |  |  | 1230
1231
[8 empty] | TOTAL STATE BONDS 143,546.01 |  |  |  |  | 1232
1233
1234
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1235
1236
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1237
1238
[8 empty] | C90CH1085CC210 82,567.01 |  |  |  |  | 1239
1240
[8 empty] | C92CH1018CC210 127,301.14 |  |  |  |  | 1241
1242
[8 empty] | C93CH535CC210 40,843.95 |  |  |  |  | 1260
1261
[8 empty] | C94CH1011CC210 108,001.19 |  |  |  |  | 1262
1263
[8 empty] | TOTAL CURRENT FUNDS 358,713.29 |  |  |  |  | 1264
1265
[8 empty] | GRAND TOTAL FUNDING 1,000,000.00 |  |  |  |  | 1266
1267
1272
PROJECT: | 265 | TSU-LAWSON HALL ROOF & UPGRADE |  | 62 | TSU-LAWSON HALL ROOF & UPGRADE | SBC: | 1660010407 | [5 empty] | 1276
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1277
|  |  | RESP LEVEL 6: | [9 empty] | 1278
1279
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1280
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1281
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1282
1283
[8 empty] | 07 MAINT., REPAIRS 0.00 104,890.38 48,849.62 |  |  |  |  | 1284
[8 empty] | 170,000.00 104,890.38 0.00 16,260.00 |  |  |  |  | 1285
1286
[8 empty] | 08 PROFESSIONAL AN 0.00 2,688.50 1,777.00 |  |  |  |  | 1287
[8 empty] | 30,000.00 16,930.23 0.00 11,292.77 |  |  |  |  | 1288
1289
[8 empty] | RESP6 LEVEL TOTAL 0.00 107,578.88 50,626.62 |  |  |  |  | 1290
[8 empty] | 200,000.00 0.00 200,000.00 121,820.61 0.00 27,552.77 |  |  |  |  | 1291
1292
1293
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1294
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1295
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1296
1297
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 304.86- 200,000.00 13,936.87 186,063.13 |  |  |  |  | 1298
1299
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 304.86- 200,000.00 13,936.87 186,063.13 |  |  |  |  | 1300
1301
[8 empty] | GRAND TOTAL FUNDING 200,000.00 |  |  |  |  | 1302
1303
1308
PROJECT: | 266 | TSU-SANITARY SEWER REPAIRS |  | 63 | TSU-SANITARY SEWER REPAIRS | SBC: | 1660010108 | [5 empty] | 1312
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1313
|  |  | RESP LEVEL 6: | [9 empty] | 1314
1315
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1316
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1317
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1318
1319
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 1320
[8 empty] | 198,000.00 0.00 0.00 198,000.00 |  |  |  |  | 1321
1322
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 0.00 |  |  |  |  | 1323
[8 empty] | 32,000.00 0.00 0.00 32,000.00 |  |  |  |  | 1324
1325
[8 empty] | RESP6 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 1326
[8 empty] | 230,000.00 0.00 230,000.00 0.00 0.00 230,000.00 |  |  |  |  | 1327
1328
1329
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1330
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1331
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1332
1333
[8 empty] | 890 INTERDEPARTMENTAL 0.00 0.00 160,000.00 0.00 160,000.00 |  |  |  |  | 1334
1335
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 0.00 70,000.00 0.00 70,000.00 |  |  |  |  | 1336
1337
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 230,000.00 0.00 230,000.00 |  |  |  |  | 1338
1339
[8 empty] | GRAND TOTAL FUNDING 230,000.00 |  |  |  |  | 1340
1341
1346
PROJECT: | 267 | TSU-HOUSING FIRE SAFETY UPGRAD |  | 64 | TSU-HOUSING FIRE SAFETY UPGRAD | SBC: | 1660010406 |  |  |  |  | x | 1350
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1351
|  |  | RESP LEVEL 6: | [9 empty] | 1352
1353
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1354
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1355
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1356
1357
[8 empty] | 08 PROFESSIONAL AN 0.00 0.00 22,577.94 |  |  |  |  | 1358
[8 empty] | 0.00 0.00 0.00 22,577.94- |  |  |  |  | 1359
1360
[8 empty] | 18 BUILDINGS 0.00 304,995.07 35,708.82 |  |  |  |  | 1361
[8 empty] | 350,000.00 304,995.07 0.00 9,296.11 |  |  |  |  | 1362
1363
[8 empty] | RESP6 LEVEL TOTAL 0.00 304,995.07 58,286.76 |  |  |  |  | 1364
[8 empty] | 350,000.00 0.00 350,000.00 304,995.07 0.00 13,281.83- |  |  |  |  | 1365
1366
1367
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1368
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1369
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1370
1371
[8 empty] | 895 INTERDEPARTMENTAL- C 0.00 200,000.00 350,000.00 200,000.00 150,000.00 |  |  |  |  | 1372
1373
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 200,000.00 350,000.00 200,000.00 150,000.00 |  |  |  |  | 1374
1375
[8 empty] | GRAND TOTAL FUNDING 350,000.00 |  |  |  |  | 1376
1377
1382
PROJECT: | 268 | TSU-INFRASTRUCTURE REPAIRS/REP |  | 65 | TSU-INFRASTRUCTURE REPAIRS/REP | SBC: | 1660010208 | [5 empty] | 1386
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1387
|  |  | RESP LEVEL 6: | [9 empty] | 1388
1389
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1390
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1391
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1392
1393
[8 empty] | 07 MAINT., REPAIRS 880,000.00 0.00 0.00 |  |  |  |  | 1394
[8 empty] | 880,000.00 0.00 0.00 880,000.00 |  |  |  |  | 1395
1396
[8 empty] | 08 PROFESSIONAL AN 120,000.00 0.00 80,300.00 |  |  |  |  | 1397
[8 empty] | 120,000.00 0.00 0.00 39,700.00 |  |  |  |  | 1398
1399
[8 empty] | RESP6 LEVEL TOTAL 1,000,000.00 0.00 80,300.00 |  |  |  |  | 1400
[8 empty] | 1,000,000.00 0.00 1,000,000.00 0.00 0.00 919,700.00 |  |  |  |  | 1401
1402
1403
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1404
1405
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1406
1407
[8 empty] | F33260C09CH1203MAINT 1,000,000.00 |  |  |  |  | 1408
1409
[8 empty] | TOTAL CURRENT FUNDS 1,000,000.00 |  |  |  |  | 1410
1411
[8 empty] | GRAND TOTAL FUNDING 1,000,000.00 |  |  |  |  | 1412
1413
1418
PROJECT: | 269 | TSU-ROOF REPAIR/REPLACEMENT SE |  | 66 | TSU-ROOF REPAIR/REPLACEMENT SE | SBC: | 1660010308 | [5 empty] | 1422
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1423
|  |  | RESP LEVEL 6: | [9 empty] | 1424
1425
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1426
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1427
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1428
1429
[8 empty] | 07 MAINT., REPAIRS 880,000.00 0.00 0.00 |  |  |  |  | 1430
[8 empty] | 880,000.00 0.00 0.00 880,000.00 |  |  |  |  | 1431
1432
[8 empty] | 08 PROFESSIONAL AN 120,000.00 0.00 0.00 |  |  |  |  | 1433
[8 empty] | 120,000.00 0.00 0.00 120,000.00 |  |  |  |  | 1434
1435
[8 empty] | RESP6 LEVEL TOTAL 1,000,000.00 0.00 0.00 |  |  |  |  | 1436
[8 empty] | 1,000,000.00 0.00 1,000,000.00 0.00 0.00 1,000,000.00 |  |  |  |  | 1437
1438
1439
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1440
1441
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1442
1443
[8 empty] | F33260C09CH1203MAINT 1,000,000.00 |  |  |  |  | 1444
1445
[8 empty] | TOTAL CURRENT FUNDS 1,000,000.00 |  |  |  |  | 1446
1447
[8 empty] | GRAND TOTAL FUNDING 1,000,000.00 |  |  |  |  | 1448
1449
1454
PROJECT: | 270 | TSU-NBIC ROOF REPAIRS |  | 67 | TSU-NBIC ROOF REPAIRS | SBC: | 1660010408 | [5 empty] | 1458
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1459
|  |  | RESP LEVEL 6: | [9 empty] | 1460
1461
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1462
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1463
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1464
1465
[8 empty] | 07 MAINT., REPAIRS 256,000.00 0.00 0.00 |  |  |  |  | 1466
[8 empty] | 256,000.00 0.00 0.00 256,000.00 |  |  |  |  | 1467
1468
[8 empty] | 08 PROFESSIONAL AN 44,000.00 0.00 26,301.00 |  |  |  |  | 1469
[8 empty] | 44,000.00 0.00 0.00 17,699.00 |  |  |  |  | 1470
1471
[8 empty] | RESP6 LEVEL TOTAL 300,000.00 0.00 26,301.00 |  |  |  |  | 1472
[8 empty] | 300,000.00 0.00 300,000.00 0.00 0.00 273,699.00 |  |  |  |  | 1473
1474
1475
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1476
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1477
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1478
1479
[8 empty] | 895 INTERDEPARTMENTAL- C 300,000.00 0.00 300,000.00 0.00 300,000.00 |  |  |  |  | 1480
1481
[8 empty] | TOTAL DEPARTMENTAL REVENUE 300,000.00 0.00 300,000.00 0.00 300,000.00 |  |  |  |  | 1482
1483
[8 empty] | GRAND TOTAL FUNDING 300,000.00 |  |  |  |  | 1484
1485
1490
PROJECT: | 271 | TSU-NETWORK INFRASTRUCTURE IMP |  | 68 | TSU-NETWORK INFRASTRUCTURE IMP | SBC: | 1660010508 | [5 empty] | 1494
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1495
|  |  | RESP LEVEL 6: | [9 empty] | 1496
1497
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1498
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1499
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1500
1501
[8 empty] | 08 PROFESSIONAL AN 100,000.00 0.00 81,958.00 |  |  |  |  | 1502
[8 empty] | 100,000.00 0.00 0.00 18,042.00 |  |  |  |  | 1503
1504
[8 empty] | 09 SUPPLIES 300,000.00 0.00 0.00 |  |  |  |  | 1505
[8 empty] | 300,000.00 0.00 0.00 300,000.00 |  |  |  |  | 1506
1507
[8 empty] | 18 BUILDINGS 900,000.00 0.00 0.00 |  |  |  |  | 1508
[8 empty] | 900,000.00 0.00 0.00 900,000.00 |  |  |  |  | 1509
1510
[8 empty] | RESP6 LEVEL TOTAL 1,300,000.00 0.00 81,958.00 |  |  |  |  | 1511
[8 empty] | 1,300,000.00 0.00 1,300,000.00 0.00 0.00 1,218,042.00 |  |  |  |  | 1512
1513
1514
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1515
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1516
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1517
1518
[8 empty] | 895 INTERDEPARTMENTAL- C 1,300,000.00 0.00 1,300,000.00 0.00 1,300,000.00 |  |  |  |  | 1519
1520
[8 empty] | TOTAL DEPARTMENTAL REVENUE 1,300,000.00 0.00 1,300,000.00 0.00 1,300,000.00 |  |  |  |  | 1521
1522
[8 empty] | GRAND TOTAL FUNDING 1,300,000.00 |  |  |  |  | 1523
1524
1529
PROJECT: | 272 | TSU-WILSON HALL INTERIORS UPGR |  | 69 | TSU-WILSON HALL INTERIORS UPGR | SBC: | 1660010608 |  |  |  |  | x | 1533
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1534
|  |  | RESP LEVEL 6: | [9 empty] | 1535
1536
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1537
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1538
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1539
1540
[8 empty] | 07 MAINT., REPAIRS 270,000.00 0.00 0.00 |  |  |  |  | 1541
[8 empty] | 270,000.00 0.00 0.00 270,000.00 |  |  |  |  | 1542
1543
[8 empty] | 08 PROFESSIONAL AN 30,000.00 0.00 0.00 |  |  |  |  | 1544
[8 empty] | 30,000.00 0.00 0.00 30,000.00 |  |  |  |  | 1545
1546
[8 empty] | RESP6 LEVEL TOTAL 300,000.00 0.00 0.00 |  |  |  |  | 1547
[8 empty] | 300,000.00 0.00 300,000.00 0.00 0.00 300,000.00 |  |  |  |  | 1548
1549
1550
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1551
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1552
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1553
1554
[8 empty] | 895 INTERDEPARTMENTAL- C 300,000.00 0.00 300,000.00 0.00 300,000.00 |  |  |  |  | 1555
1556
[8 empty] | TOTAL DEPARTMENTAL REVENUE 300,000.00 0.00 300,000.00 0.00 300,000.00 |  |  |  |  | 1557
1558
[8 empty] | GRAND TOTAL FUNDING 300,000.00 |  |  |  |  | 1559
1560
1565
PROJECT: | 273 | TSU-CENTER FOR AG BIOTECHNOLOG |  | 70 | TSU-CENTER FOR AG BIOTECHNOLOG | SBC: | 1660010708 | [5 empty] | 1569
[10 empty] | RESP LEVEL 5: | 99 STRUCTURE ROLLOVER TSU |  | 1570
|  |  | RESP LEVEL 6: | [9 empty] | 1571
1572
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1573
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1574
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1575
1576
[8 empty] | 08 PROFESSIONAL AN 75,000.00 0.00 0.00 |  |  |  |  | 1577
[8 empty] | 75,000.00 0.00 0.00 75,000.00 |  |  |  |  | 1578
1579
[8 empty] | RESP6 LEVEL TOTAL 75,000.00 0.00 0.00 |  |  |  |  | 1580
[8 empty] | 75,000.00 0.00 75,000.00 0.00 0.00 75,000.00 |  |  |  |  | 1581
1582
1583
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1584
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1585
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1586
1587
[8 empty] | 895 INTERDEPARTMENTAL- C 75,000.00 0.00 75,000.00 0.00 75,000.00 |  |  |  |  | 1588
1589
[8 empty] | TOTAL DEPARTMENTAL REVENUE 75,000.00 0.00 75,000.00 0.00 75,000.00 |  |  |  |  | 1590
1591
[8 empty] | GRAND TOTAL FUNDING 75,000.00 |  |  |  |  | 1592
1593
[8 empty] | 1 | STATE OF TENNESSEE ADMIN AGENCY 332.60 |  |  |  | 1594
1598
PROJECT: | 210 | UNALLOTTED SAVINGS |  |  |  | SBC: | N/A | [5 empty] | 1602
[10 empty] | RESP LEVEL 5: | 10 UNALLOTTED SAVINGS |  | 1603
1604
[8 empty] | ALLOTMENT EXPENDITURES ENCUMBRANCES/ |  |  |  |  | 1605
[8 empty] | MAJ TOTAL TOTAL YR-TO-DATE/ YR-TO-DATE REQUISITIONS UNENCUMBERED |  |  |  |  | 1606
[8 empty] | OBJ DESCRIPTION APPROPRIATION UNALLOTED PRJ-TO-DATE PRJ-TO-DATE PRJ-TO-DATE ALLOTMENT |  |  |  |  | 1607
1608
[8 empty] | 07 MAINT., REPAIRS 0.00 0.00 0.00 |  |  |  |  | 1609
[8 empty] | 0.00 0.00 0.00 0.00 |  |  |  |  | 1610
1611
[8 empty] | RESP5 LEVEL TOTAL 0.00 0.00 0.00 |  |  |  |  | 1612
[8 empty] | 50,312.50 50,312.50 0.00 0.00 0.00 0.00 |  |  |  |  | 1613
1614
1615
[8 empty] | DEPARTMENTAL REVENUE |  |  |  |  | 1616
[8 empty] | ------------ YEAR-TO-DATE ------------ --------------------- PROJECT-TO-DATE -------------------- |  |  |  |  | 1617
[8 empty] | SOURCE DESCRIPTION ESTIMATE ACTUAL ESTIMATE ACTUAL UNREALIZED |  |  |  |  | 1618
1619
[8 empty] | 880 CURRENT SERVICES 0.00 0.00 50,312.50 50,312.50 0.00 |  |  |  |  | 1620
1621
[8 empty] | TOTAL DEPARTMENTAL REVENUE 0.00 0.00 50,312.50 50,312.50 0.00 |  |  |  |  | 1622
1623
1624
[8 empty] | STATE BONDS |  |  |  |  | 1625
1626
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1627
1628
[8 empty] | B02CH852AVON 11,600,000.00- |  |  |  |  | 1629
1630
[8 empty] | B02CH852CO 11,600,000.00 |  |  |  |  | 1631
1632
[8 empty] | B86CH875CLAY 12,052.66- |  |  |  |  | 1633
1634
[8 empty] | B88CH945CLAY 43,655.56- |  |  |  |  | 1635
1636
[8 empty] | B88CH945COLLEG 43,655.56 |  |  |  |  | 1637
1638
[8 empty] | B90CH947 13,326.94 |  |  |  |  | 1639
1640
[8 empty] | B90CH947ADMIN 276,484.73- |  |  |  |  | 1641
1642
[8 empty] | B90CH947AGRIC 237,419.87 |  |  |  |  | 1643
1644
[8 empty] | B90CH947INFRA 14,937.35- |  |  |  |  | 1645
1646
[8 empty] | B90CH947POWER 14,937.35 |  |  |  |  | 1663
1664
[8 empty] | B90CH947UTILIT 25,737.92 |  |  |  |  | 1665
1666
[8 empty] | B96CH952AVON 283,735.92- |  |  |  |  | 1667
1668
[8 empty] | B96CH952BOYD 283,735.92 |  |  |  |  | 1669
1670
[8 empty] | B96CH952ELL I 19,196.77- |  |  |  |  | 1671
1672
[8 empty] | B96CH952HARNED 15,786.95 |  |  |  |  | 1673
1674
[8 empty] | B96CH952INDUST 3,409.82 |  |  |  |  | 1675
1676
[8 empty] | F33260B86CH875UNALL 12,052.66 |  |  |  |  | 1677
1678
[8 empty] | TOTAL STATE BONDS 0.00 |  |  |  |  | 1679
1680
1681
[8 empty] | STATE CURRENT FUNDS |  |  |  |  | 1682
1683
[8 empty] | DESCRIPTION TRANSACTION AMT |  |  |  |  | 1684
1685
[8 empty] | C84CH14CAMPUS 697.96 |  |  |  |  | 1686
1687
[8 empty] | C84CH14MGT 697.96- |  |  |  |  | 1688
1689
[8 empty] | C85CH4MGT 796.96- |  |  |  |  | 1690
1691
[8 empty] | C85CH467ENERGY 16,168.18 |  |  |  |  | 1692
1693
[8 empty] | C85CH467MGT 16,168.18- |  |  |  |  | 1694
1695
[8 empty] | C86CH937ADMIN 477,955.48- |  |  |  |  | 1696
1697
[8 empty] | C86CH937ALBION 35,000.00- |  |  |  |  | 1698
1715
[8 empty] | C86CH937DORM 235,711.39 |  |  |  |  | 1716
1717
[8 empty] | C86CH937LAND 283,816.89 |  |  |  |  | 1718
1719
[8 empty] | C86CH937MGT 7,475.34- |  |  |  |  | 1720
1721
[8 empty] | C87CH457 MGT 8,387.16- |  |  |  |  | 1722
1723
[8 empty] | C87CH457FAC 24,939.00- |  |  |  |  | 1724
1725
[8 empty] | C87CH457GOODWI 10,525.79 |  |  |  |  | 1726
1727
[8 empty] | C87CH457MGT 28,235.34- |  |  |  |  | 1728
1729
[8 empty] | C87CH457OUTSID 33,326.16 |  |  |  |  | 1730
1731
[8 empty] | C87CH457PCB 17,709.55 |  |  |  |  | 1732
1733
[8 empty] | C89CH563 MGT 17,897.63- |  |  |  |  | 1734
1735
[8 empty] | C89CH563AGRIC 53,000.00 |  |  |  |  | 1736
1737
[8 empty] | C89CH563ALUMNI 19,814.04 |  |  |  |  | 1738
1739
[8 empty] | C89CH563ASBEST 136,729.43 |  |  |  |  | 1740
1741
[8 empty] | C89CH563BOILER 88,824.96 |  |  |  |  | 1742
1743
[8 empty] | C89CH563BUSINE 103,714.91 |  |  |  |  | 1744
1745
[8 empty] | C89CH563CHEM 14,383.61 |  |  |  |  | 1746
1747
[8 empty] | C89CH563ELLI 8,295.60- |  |  |  |  | 1748
1749
[8 empty] | C89CH563GRAVIT 36,597.57 |  |  |  |  | 1750
1751
[8 empty] | C89CH563HVAC 65,151.43 |  |  |  |  | 1768
1769
[8 empty] | C89CH563LANDSC 14,993.10 |  |  |  |  | 1770
1771
[8 empty] | C89CH563LIBR 28,663.47 |  |  |  |  | 1772
1773
[8 empty] | C89CH563MASTPL 14,185.60 |  |  |  |  | 1774
1775
[8 empty] | C89CH563MGT 715,122.44- |  |  |  |  | 1776
1777
[8 empty] | C89CH563STEAM 91,360.82 |  |  |  |  | 1778
1779
[8 empty] | C89CH563STORAG 37,714.03 |  |  |  |  | 1780
1781
[8 empty] | C89CH563STUDEN 12,355.02 |  |  |  |  | 1782
1783
[8 empty] | C90CH1085BROWN 60,337.02 |  |  |  |  | 1784
1785
[8 empty] | C90CH1085CADD 12,956.38 |  |  |  |  | 1786
1787
[8 empty] | C90CH1085CAMCT 67,041.75 |  |  |  |  | 1788
1789
[8 empty] | C90CH1085CLAY 35,000.00 |  |  |  |  | 1790
1791
[8 empty] | C90CH1085ELLI 31,663.09- |  |  |  |  | 1792
1793
[8 empty] | C90CH1085ENG 22,499.69 |  |  |  |  | 1794
1795
[8 empty] | C90CH1085FIRE 237,233.52 |  |  |  |  | 1796
1797
[8 empty] | C90CH1085HANKA 82,567.01- |  |  |  |  | 1798
1799
[8 empty] | C90CH1085INFRA 260,384.53- |  |  |  |  | 1800
1801
[8 empty] | C90CH1085KEAN 5,522.34- |  |  |  |  | 1802
1803
[8 empty] | C90CH1085MGT 140,433.94- |  |  |  |  | 1820
1821
[8 empty] | C90CH1085RENO 4,394.49 |  |  |  |  | 1822
1823
[8 empty] | C90CH1085UPGRA 82,567.01 |  |  |  |  | 1824
1825
[8 empty] | C92CH1018ADMIN 273,000.00- |  |  |  |  | 1826
1827
[8 empty] | C92CH1018ELLI 164,555.88- |  |  |  |  | 1828
1829
[8 empty] | C92CH1018HANKA 127,301.14- |  |  |  |  | 1830
1831
[8 empty] | C92CH1018INFRA 91,137.52- |  |  |  |  | 1832
1833
[8 empty] | C92CH1018LAND 493,205.40 |  |  |  |  | 1834
1835
[8 empty] | C92CH1018MGT 1,328.49- |  |  |  |  | 1836
1837
[8 empty] | C92CH1018OPER 8,004.63 |  |  |  |  | 1838
1839
[8 empty] | C92CH1018OPERA 45,000.00- |  |  |  |  | 1840
1841
[8 empty] | C92CH1018SITE 134,482.68 |  |  |  |  | 1842
1843
[8 empty] | C92CH1018UTIL 20,301.83 |  |  |  |  | 1844
1845
[8 empty] | C92CH1018WILSO 38,724.42 |  |  |  |  | 1846
1847
[8 empty] | C93CH1018ADMIN 3,005.57 |  |  |  |  | 1848
1849
[8 empty] | C93CH1018DORM 58,786.87 |  |  |  |  | 1850
1851
[8 empty] | C93CH1018DOWN 2,545.43 |  |  |  |  | 1852
1853
[8 empty] | C93CH1018WATSO 1,340.76 |  |  |  |  | 1854
1855
[8 empty] | C93CH535 600.00 |  |  |  |  | 1872
1873
[8 empty] | C93CH535 MGT 2,797.40- |  |  |  |  | 1874
1875
[8 empty] | C93CH535ADMIN 69.77 |  |  |  |  | 1876
1877
[8 empty] | C93CH535HANKAL 40,843.95- |  |  |  |  | 1878
1879
[8 empty] | C93CH535MCCORD 22,707.05- |  |  |  |  | 1880
1881
[8 empty] | C94CH1011HANKA 108,001.19- |  |  |  |  | 1882
1883
[8 empty] | C94CH1011SITE 108,001.19 |  |  |  |  | 1884
1885
[8 empty] | F33260C85CH4 UNALL 796.96 |  |  |  |  | 1886
1887
[8 empty] | F33260C86CH937UNALL 902.54 |  |  |  |  | 1888
1889
[8 empty] | F33277C89CH563AGRIC 21,699.66 |  |  |  |  | 1890
1891
[8 empty] | F33277C89CH563CLAY 478.02 |  |  |  |  | 1892
1893
[8 empty] | F33277C89CH563STORAG 625.00 |  |  |  |  | 1894
1895
[8 empty] | F33277C90CH1085CAMCT 11,381.05 |  |  |  |  | 1896
1897
[8 empty] | F33277C92CH1018WILSO 7,604.07 |  |  |  |  | 1898
1899
[8 empty] | F35540C89CH563STORAG 1,025.00 |  |  |  |  | 1900
1901
[8 empty] | T33260C90CH1085MGT 12,840.00- |  |  |  |  | 1902
1903
[8 empty] | TOTAL CURRENT FUNDS 0.00 |  |  |  |  | 1904
1905
[8 empty] | GRAND TOTAL FUNDING 50,312.50 |  |  |  |  | 1906